Care Quality Work Plan

June 2024-May 2025

Care Quality Work Plan	1

Goal 1: Collaborate to Advance the SHIP	1

Objective 1: Create and maintain a functional work group focused on SHIP objectives.	1

Objective 2: Identify responsible parties for each SHIP strategy.	2

Goal 2: Increase Healthy Behaviors	3

Objective 1: Provide guidance to organizations in their journey to align with the SHIP.	3

Goal 3: Improve Early Detection Through Routine Screenings and Early Interventions	4

Objective 1: Identify ways to improve adherence to healthcare recommendations for routine screenings.	4

# Goal 1: Collaborate to Advance the SHIP

## Objective 1: Create and maintain a functional work group focused on SHIP objectives.

| ##### ACTIVITIES How are we going to accomplish the objective? | ##### WHO Who is responsible for the activities? | ##### WHEN When will the activity begin and end? | ##### OUTCOMES What are the desired results? | ##### EVALUATION How are we going to measure the outcome(s)? | ##### ACTION STEPS | ##### COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| Hold quarterly workgroup meetings. | Workgroup Co-Chairs; Contracted Facilitator | June 2024- May 2025 | The Access to Care workgroup met each quarter during the time period. | In 100% of the quarters during the time period there is a documented workgroup meeting. | - Identify Co-chairs - Schedule quarterly meetings - Document meetings - Manage the document archives. |  |
| Conduct annual workgroup member contact update. | Contract Facilitator | June 2024-May 2025 | The workgroup member contact information is up to date. | 100% of contact information is updated annually, during the time period. | - Identify an accessible location for contact information. - Determine an annual date to request updates. - Request updates. - Update contact information. |  |
| Create Goal sub workgroups. | Workgroup members; Contract Facilitator | Nov 2024-May 2025 | Each goal within the priority area has a dedicated sub workgroup identified and functioning. | 100% of goals within the priority area has a goal sub workgroup identified. | - Review need with co-chairs. - Offer self-assignment to goal sub workgroups to workgroup members. - Maintain the sub workgroup member lists. |  |
| Create an annual report of workgroup activities. | Co-Chairs; Contract Facilitators | 2025-2029 Annually | An annual report will be created and shared with the SHIC. | 100% of years in the time period have evidence of a workgroup annual report that was shared with the SHIC. | - Gather information for the annual report. - Write the annual report. - Share the annual report with the SHIC. - Archive and maintain the reports. |  |

## Objective 2: Identify responsible parties for each SHIP strategy.

| ##### ACTIVITIES How are we going to accomplish the objective? | ##### WHO Who is responsible for the activities? | ##### WHEN When will the activity begin and end? | ##### OUTCOMES What are the desired results? | ##### EVALUATION How are we going to measure the outcome(s)? | ##### ACTION STEPS | ##### COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| Develop and maintain a list of strategies for each goal in the priority area and identify person/org/communities who are responsible for these strategies. | Workgroup members; Co-Chairs; Contract Facilitator | June 2024-May 2025 | A comprehensive list of strategies and responsible parties is developed and maintained. | A strategies list with responsible parties is evidenced. | 1. Develop a list of strategies 2. Gather a list of responsible parties. 3. Share with other work groups and SHIC coalition. 4. Identify the party responsible for maintaining the list throughout the SHIP. | SD-DOH led strategies to be highlighted. |

# Goal 2: Increase Healthy Behaviors

## Objective 1: Provide resources to promote health partner alignment with SHIP goals.

| ##### ACTIVITIES How are we going to accomplish the objective? | ##### WHO Who is responsible for the activities? | ##### WHEN When will the activity begin and end? | ##### OUTCOMES What are the desired results? | ##### EVALUATION How are we going to measure the outcome(s)? | ##### ACTION STEPS | ##### COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| Analyze current DOH programs. | Co-Chairs; Contract Facilitator | Nov 2024-May 2025 | A comprehensive report detailing the DOH programs- location, outcomes/impact, current state and planned future state. | A comprehensive report is received from DOH | - Gather the data elements to be included in the request. - Request the report from DOH. - Review the DOH report. - Create an analysis- recommendations and next steps. |  |
| Provide programming/service best practice toolkit(s) to impact healthy choices. | Co-Chairs; Workgroup members; Contract Facilitator | Nov 2024-May 2025 | Toolkits are created and distributed to organizations in counties of most need of successful programming/services | One best practice toolkit is created and distributed. | - Identify successful programs. - Request successful program to present to the CQ workgroup. - Interview the programs leaders to obtain information on framework, execution, monitoring, and incentives. - Create a toolkit. - Identify areas of need based on data analysis. - Distribute toolkit. | 11/22/24- Co Chairs requested the SD Cardiovascular Collaborative to present at the next CQ Workgroup meeting. |
| Gather insights from high-risk populations. | Co-Chairs; Workgroup members; Contract Facilitator | Nov 2024-May 2025 | The workgroup obtains insights from high-risk populations that inform the workgroup efforts. |  | - Identify the target high-risk populations through data analysis. - Identify parties to assist in developing taskforce or the like of these populations. - Create charter, purpose statement, and expectations for the task force. - Solicit participants. - Gather participants. - Collect insights - Report to SHIC. | 11/22/24- Co Chairs initiated development of a high school task force to address youth outcomes. |

# Goal 3: Improve Early Detection Through Routine Screenings and Early Interventions

## Objective 1: Identify best practices to improve adherence to healthcare recommendations for routine screenings.

| ##### ACTIVITIES How are we going to accomplish the objective? | ##### WHO Who is responsible for the activities? | ##### WHEN When will the activity begin and end? | ##### OUTCOMES What are the desired results? | ##### EVALUATION How are we going to measure the outcome(s)? | ##### ACTION STEPS | ##### COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| Identify the gap between the healthcare recommendations for screenings and high-risk populations lack of adherence | Co-Chairs; Workgroup members; Contract Facilitator | Nov 2024-May 2025 | Meaningful information gathered from high-risk populations. |  | - Identify the high-risk population with which to work. - Identify groups that can gather or provide relevant information on the topic(s). - Meet with the groups. - Create a report on insights gathered. - Distribute the report. | 11/22/24 Co-Chairs requested cross collaboration with the Behavioral Health Workgroup to begin discussions on gathering information on behavioral health patients. |